

**THE PRESIDENCY**

**Executive Office of the President**

**Directorate of National Cohesion and Values**

**ROADMAP TO THE 6TH ANNUAL PRESIDENT’S STATE OF THE NATION ADDRESS TO PARLIAMENT, 2018**

The Directorate of National Cohesion and Values has prepared a road map of activities preceding the 2018 State of the Nation Address. The road map comprises the 2018 Annual Presidents Report on Measures Taken and Progress Achieved in the Realisation of National Values and Principles of Governance [**Article 132(1)(c)(i)(ii)**], Progress made in the Fulfillment of International Obligations of the Republic [**Article 132(1)(c)(iii)**] and the State of National Security of Kenya [**Article 240(7)**].

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NO.** | **NAME OF ACTIVITY** | **ACTION BY** | **START DATE** | **END DATE** |
|  | Training of additional Focal Point Persons from Ministries, Departments and Agencies (MDAs) | Directorate of National Cohesion and Values | April, 2018 | March, 2019 |
|  | Training of additional National Values and Principles of Governance Committees from the various Ministries, Departments and Agencies (MDAs) | Directorate of National Cohesion and Values | April, 2018 | June, 2019 |
|  | Issuance of circular by the Head of Public Service requiring MCDAs to submit reports. | Head of Public Service, PS/ Interior, PS/ MFA and  Directorate of National Cohesion and Values | November, 2018 | December, 2018 |
|  | Briefing of focal point persons and Launch of 2018 President’s Reporting Cycle | Steering Committee and Secretariat | 4th, December, 2018 | 7th,December, 2018 |
|  | Submission of reports from Ministries, Counties, Departments and Agencies (MCDAs) | Joint Secretariat | 10th December, 2018 | 15th, January, 2019 |
|  | * Coding, collation and analysis of the submitted reports from Ministries, Counties, Departments and Agencies (MCDAs) * Commencement of compilation of the State of Security & the International Obligations Report. | Joint Secretariat   * PS/Interior * PS//MFA * Directorate of National Cohesion and Values | 16th January, 2019 | 1st, February, 2019 |
|  | Compilation of the initial Draft of the three (3) Annual President’s reports | * Steering Committee and * PS/Interior * PS/MFA | 4th February, 2019 | 8th February, 2019 |
|  | Presentation of the Draft Annual President’s Report on National Values & Principles of Governance to Focal Point Persons from Ministries, Counties, Departments and Agencies (MCDAs) and representatives of other public institutions for verification and validation | * Secretariat and Steering committee | 18th February, 2019 | 19th February, 2019 |
|  | Incorporation of the input made by the Focal Point Persons from Ministries, Counties, Departments and Agencies (MCDAs) & representatives of other public institutions on the draft Annual President’s report | * Secretariat and Steering committee | 20th February, 2019 | 22nd February, 2019 |
|  | Securing a date for the State of the Nation Address by H.E the President | * Head of Public Service and Clerk of the National Assembly | 25th February, 2019 | 27th February, 2019 |
|  | High level Consultative Forum including the Principal Administrative Secretary (PAS) and the Office of the Head of Public Service, on the 2018 Annual President’s Report | * Steering Committee and Secretariat | 4th March, 2019 | 5th March, 2019 |
|  | Incorporation of input from high level Consultative Forum/ PAS & Office of the Head of Public Service | * Steering Committee and Secretariat | 6th March, 2019 | 8th March, 2019 |
|  | Presentation of the three (3) Draft Reports to the National Security Advisory Committee (NSAC) | * DNC&Vs * CS/MFA * CS/Interior | 12th March, 2019 | 13th March 2019 |
|  | Incorporation of input made on the three (3) Draft Reports by the National Security Advisory Committee (NSAC) | * DNC&Vs * CS/MFA * CS/Interior | 14th March, 2019 | 15th March 2019 |
|  | Submission of the final Reports to the Office of the Head of Public Service | * Head of Public Service * Directorate of National Cohesion and Values * MFA * MoI &CNG | 18th  March, 2019 | 19th March, 2019 |
|  | Briefing of H.E the President and National Security Council (NSC) on the three (3) final Reports | * Head of Public Service * Directorate of National Cohesion and Values * MFA * MoI &CNG | 20th March, 2019 | 22nd March, 2019 |
|  | Incorporation of input made on the three (3) Draft Reports made during the briefing of H.E the President and National Security Council (NSC) | * Head of Public Service * Directorate of National Cohesion and Values * MFA * MoI &CNG | 25th March, 2019 | 25th March, 2019 |
|  | Presentation of the reports to Government Press for printing | * Directorate of National Cohesion and Values * MFA * MoI&CNG | 26th March, 2019 | 26th March, 2019 |
|  | Submission of copies of the printed final Reports to the Office of the Head of Public Service | * Directorate of National Cohesion and Values * MFA * MoI &CNG | 27th  March, 2019 | 27th March, 2019 |
|  | State of the Nation Address to Parliament (both Chambers) by H.E the President | * H.E. the President; * Speaker of the National Assembly; * Head of Public Service; and * Clerk of the National Assembly * DNC & V | 28th March, 2019 | 28th March, 2019 |
|  | Gazettement of the 2018 Annual President’s Report on National Values and Principles of Governance | * Office of the Head of Public Service * DNC & V | 29th March, 2019 | 5th April, 2019 |
|  | Dissemination, issuing of guidelines on the implementation of H.E the President’s Government’s commitments and Way Forward for 2018 | Office of the Head of Public Service and the Directorate of National Cohesion and Values | April, 2019 | March, 2020 |